## OW_Bandit_v1
Layout / Assembly					Environment preparation					Buy
create script for burning via UART					OK
Create script for burning via UART UART					OK		install avrdude					OK
Create ICSP circuit for Atmega 2560					OK		Add installation step-by-step instruction to README.MD					OK		choose screws for PCB holding					OK
Add two leds for testing					OK		Test, how burning is working from Clion					OK
Create debug output on layout board					OK		Test, how bootloader burning is working					OK		buy 24cm01					OK
Create UART output on layout board					OK		Include binutils in avrdude version in README.MD					OK		charger for battery					ok
Add 16Mhz crystall					OK					Order 12 mhz crystall smd					ok
Create reset circuit					OK		Mention elements list in README.md					77		order tp4056 chargers					OK
Create and test 1wire emulator					OK		create bill of materials					77		order ch340 usb-uart converteri					OK
Create and test 1wire reader					OK		proveritj naschet gcc-avr svjazki – ssilka v browsere					OK		order jst connectors					OK
Create and test 1wire writer					OK		dopisatj kakije eshe programmi ustanavlival					OK		order jst sockets					OK
Create and test led blink					OK		ukazatj vremja zarjadki					77		mc34063					OK
Create and test vibromotor					OK		ukazatj vremja raboti ot odnoj zarjadki – standby					77		order smd electrolytes (caps)					ok
Create and test buzzer					OK		ukazatj vremja raboti ot odnoj zarjadki –active usage					77		order smd rezistors for nominal <1 Ohm					ok
create buzzer/vibromotor assembly					OK					Order smd inductors					ok
Test its work					OK		create tutorial about how to compile the project					77		buy battery					ok
Draw on circuit diagram					OK		youtube video demonstration					77		order connector for bl-4c batteries					ok
Create tp4056 assembly					OK		Add current consumption info					77		order 2n7000 smd [ordered 2n7002]					OK
Test its work					OK					order 2n2222					ok
Draw on circuit diagram					OK		Add cmake installation description					77		order mosfet sortiment					not needed
Create DC/DC converter assembly					OK			sudo apt install cmake-curses-gui					relay 5v order					OK
Test its work					OK
Draw on circuit diagram					OK		goto OW_Bandit/cmake/ArduinoToolchain.cmake and there:					FPC wires order					OK
Create cp2102 / ch340 usb/uart converter assembly					OK			set ARDUINO_SDK_PATH				not needed		FPC socketi – male, female zakazatj					OK
Test its work					OK		install arduino – sudo apt install arduino					77
Draw on circuit diagram					OK					order hef 4066					OK
Create max17043 assembly					OK
Test its work					OK		PCB					Problems
Draw on circuit diagram					OK
Create hc-06 assembly					OK		on schematic mark crystall with two caps					OK		program is not working after burning					OK
Test its work					OK		Check all elements package – should be SMD					OK			Xtal ?				OK
Draw on circuit diagram					OK
Create eeprom assembly 24c32					OK					Test crystal work on other arduino boards with oscilloscope					OK
Test its work					OK					test fuses		yes, it were fuses			OK
Draw on circuit diagram					OK
restore periphery on layout board					OK		add leds tx/rx on					OK		https://soc.ninja/documentation/programming-atmega2560-with-arduino-uno-or-mega/#comment-159
finalize bootloader burn functionality on atmega2560					OK
Create functionality to burn firmware via UART					OK		download datasheets on all IC and add to project					77
Create bling tes					OK		create device layout assembly					OK
Find circuit diagram for atmega2560 mini board					OK		create photos of case layout					OK		on mega2560 after bootloader burning the program could be burned in via UART only once
create circuit diagram in easyEda					OK		commit everything in github					OK			current overload ?				not tested
test how code compiles					OK		Why during firmware burl Ulock is needed?					77			reset circuit ?				looks like this one
Rewrite program for Atmega2560					OK
Make test launch on atmega2560					OK					problem was in capacitor between RESET pin and gnd				no
Refactor project structure (folders, etc)					OK		add to README location with scripts					77		https://forum.arduino.cc/index.php?topic=393392.0
Create scripts for assembly, cleanup and project build					OK		add circuit diagram to projekt					77
Add generated files to gitignore					OK		Add PCB schema to project					77
Finalize the functionality of left functions of menu					OK					problem in 100nf cap between DTR and RESET				no
Clarify info about HC06 led					OK
hc-06 –retrace the circuit diagram on PCB					OK		find the name of connector for battery					OK
Add constancts to code					OK		find which type of battery to use			BL-5C ili BLC-2		OK		combines stable work of ch340 and hc-06 is impossible on one port
Create function for first start and setting up the HC06 params					OK					move hc-06 to another serial port and test its work					OK
Store settings in MCU internal EEPROM					OK					check how it was implemented on arduino mega arduino mega					not needed
On startup check the internal memory of MCU for stored settings presence					tracing pcb keep in mind hole positions					OK		try to change resistors in ch340 circuit
initialize HC06 if absent					OK					became a bit better changing resistor from 1kOhm to 330 Ohm in hc06 circuit
hc-06 trace key input					OK		try burn MCU via UART module with connected HC-06					OK		problem disappeared after changing rezistors on CH430 from 1KOhm to 220 Ohm
hc-06 connect to key pin					OK		hc-06 key and power pins – add to circuit diagram and PCB					OK
create power on pin for powering hc06					OK		iButton emulator - trace in PCB					OK		Completely remove resistors on rx and tx pins for HC06 and CH340					not needed
trace it on motherboard					OK		iButton reader - trace in PCB					OK
Create C++ module for HC-06					OK		Buzzer - trace in PCB					OK		problem solved by moving HC-06 to another port					OK
Create method for tracking memory status					OK		add all related diodes in circuitDiagram and PCB					OK
Create method for tracking max17043 status					OK		draw package for ow_slave and ow_master					zz
Buzzer – beacon function – make it separate					OK		ad power switch					OK
buzzer beep ok					OK		add power led					OK		errors appeared on 115200 baudrate
buzzer beep error					OK		add dimentions for motherboard					OK		menu visualizes twice
Drag there functions for vibromotor					OK		add dimenttions for power board					OK		maybe it is related with extra signs sending					77
HC-06 change baudrate to 115200					OK		make v-groove or something related on PCB					OK
Create fucntion for visualizing status of internal memory					OK		sign PCB’s					OK
				power unit board				OK
motherboard tests					OK			mcu board				OK
				top				OK		system status – displayed keys number is negative and not correct					OK
	+ EEPROM24C32				OK			bottom				OK
	+ Internal EEPROM				OK		make icsp header be surface mount					not needed
	+ Bluetooth				OK		find smd crystal , smalledr size					OK
	+ Vibromotor				OK		finish tracing charging leds sockets					OK		MCU eeprom data is erased after reset					OK
	+ UART_CH340				OK		trace hc-06					OK			Problem was in variable type and cell distance in memory
				trace max17043					OK
	+ _MC34063				OK		trace tp4056					OK
	+ _TP4056				OK		trace mc34063					OK
	+ MAX17043				OK		trace ch340					OK
				trace mcu					OK
connect all elements of layout tpgether					OK		move major part of electronic components to the other side of PCB’s					OK
test its work					OK		Trace socket FPC					OK
				trace 5v line					OK
after assembly check the battery outputs – shouldn’t be 5V					OK		trace gnd line					OK
				trace battery connectors					OK
Test DC/DC converter work with stabilizer connected to output					OK		put all elements on related boards					OK
with stab became better					sign all leds on PCB			POWER_SW_OUT		OK

Test DC/DC converter work with LC filter connceted to output					OK
make coil 1uH					OK
with coil became much better					find all models for elements (3d view)					OK		Program
				OK
Test DC/DC converter work with LC filter connected to output with load					USB type b soket – needed to change to usb mini socket					OK		Function system boot log move to system info [0]					OK
	filter should be detached				OK					function check battery status should be renamed in system status					OK

Ensure after complete assembly that everything is working when all modules are connected					checkout recommendations for mc34064 tracing from datasheet					not needed
				OK					unify some functions – append and overwrite					77
				trace alert pin to MCU or remove it			removed		OK
Move buzzer on another pin – after burnirts buzzing					OK		align all titles near elements					OK		create constants for functions parameters (where overwrite=true)					77

Tp4056 + battery + usb power + mc34063 + icsp + load					77		Add near battery socket plus and minus sign					OK		create library for messaging					77
all except burning via UART					After recording make automatic \r\n				77
				Make mob.phone terminal resolution setup				77
Maybe it makes sence to add MOSFET on RX pin from bluetooth module or use relay					not needed		Make traces for 5v line wider					not needed
test all layout work with diode on DC/DC output					OK		make traces wider for tp4056					not needed		on startup show firmware version					not needed
	output voltage is too low – recalculate resistors nominals			pereschitajt nominali rezistorov			make traces wider for gnd line					not needed		firmware version should be also in system status					OK
check possibility to add additional eeprom for storing additional text messages related to keys (iButton)					make traces wider for bat+ and bat-					not needed
				OK		make traces wider for mc34063					not needed		display memory when no keys –show msg that key storage is empty					OK
AT24cm02 i2c flash 2mbit		512 bytes for 1 key		4.22eur				not needed, because it’s ok to use for 1 A 0.25mm wide traces
AT24cm01 i2c flash 1mbit		256 bytes for 1 key		1.70eur					make vibro when key is recorded					OK
	connect A0 to Vdd
Create layout forat24cm01 eeprom					OK					Ignore +DISC:SUCCESS message from HC06					77
check its work					OK
draw on circuit diagram / PCB					OK					use copy protection fuses					77
create test function in a code					OK
Initialization results store into menu → system status					77		make additional mini pcb for power switch					OK		Code refactoring					77
create journal feature					77		find a way how to solder it					OK
				Button case should be 10mm deep into pcb					OK		check how the values like 512 and more stored in internal memory					OK

Enclosure layout					deal with warnings in project during compile					77
				make 3d models for the elements					OK
reset button					OK					Create testing matrix					77
mini usb soket for charging and programming / debuging					OK
charging led / charged led – 2 color through hole					OK					Creat invitation string $> orOW_Bandit>					not needed
transmission led through hole					OK		create 3d model for mattery socket					OK		ewmKW MWNU					77
buzzer					OK		create 3d model for ow_slave					zz
power switch					OK		create 3d model for ow_master					zz		create journal feature for key info					77
OneWire iButton socket					OK		create 3d model for buzzer					OK
iButton connector					OK					check if memory stored settings cleanup function exists					77
soket for icsp burning					OK

power led		Will use led inside of OW-slave socket			not needed					create elements list / module (e.g.dc/dc converter, list					77
as power led we’ll use led from HC-06					USB socket too big					if its related elements (c21, c22), and metion position on board
move iButton male to center					OK			change to usb micro				OK
move iButton female to center					OK
move usb type b on another side, compating to leds					OK		make 3d models for the elements					OK
				make caps/resistors of one size – 0603					OK		After plugging usb cable bluetooth disables					because of voltage drop
	Create serial line commutator using4066 ic + tranzistor				not needed		Remake footprint for socket for battery (too small)					OK					should be tested
	create layout and check its work				not needed
	trace it on pcb				not needed
	Create buttons/switches for enabling it on 3rd pcb				not needed		create pcb for FPC cable– solder it on pcb					not needed
	switch for uart / hc06 – make like power switch, with pinhole and without capsdelatj kak power switch, tolko otverstije malenkoje I knopku naruzhu ne vivoditj				not needed
				mark cutting line on PCB					OK		Problems with HC-06 power supply – 4v goes to stabilizer instead of 5V – maybe this voltage drop because of too high current consumption
				– gde budut OneWire soketi dlja slave I master					OK
				otsilajutsa kakie-to levie simvoli na hc-06 – menu pojavljajetsa neskolko raz – vozmozhno iz-za pitanija

	trace leds on 3rd pcb – charging and ready				OK		Mark position of vibromotor on opposite side					OK		LDO AMS1117 3.3v too big voltage drop (about1.1 v)– find substitute

	trace outputs on pcb for UART1 and UART2				not needed
				create separate pcb for periphery					OK
	move icsp socket to another place on board				OK
				make cut-out on pcb					OK
	Move battery socket to the right/left				OK					after disabling power in circuit 1,3v voltage is present – because of max17043 is connected to battery

	move the battery itself – not enough room				OK		find a way how to import models					OK		During keys emulating taking it from memory doesn’t iniorm if memory is impty					77

	move battery to opposite pcb				OK		checkout a way of unmasked copper					not needed

	move relay to another place – is in the way of battery				OK		Solder 5 tantal (tantal) and test its work on layout					77
				increase cap nominal on DC/DC output					didn’t help
	move socket for battery				OK
				clarify, why HC-06 is so big current consumption pulsations					hc-06 is in search
	add socket for ow-slave on 3rd pcb ow_emulator				OK					ch340 adds pulsations
				capacitor		order lower nominal caps (smd)			OK				caps almost doesn’t help
	ow_host soket move to the edge				OK				500uF					looks like DC/DC is too weak			?
				400 uf
	create smd buzzer and move it to the opposite side of pcb				OK				300 uf					after HC-06 pairing pulsations disappears
				250uf
create initiali layout assembly using large details					OK				200 uf
test the sizes of components				Complete fuckup	OK				or create capacitor battery
				cap is too high
find solution for sticking battery to the pcb					OK			connect it to board via longer wires					buy glue for papel (for case layout)					ok
	2-side tape					make hole in opposite PCB					Buy 2.54 pin header 2x40 for ICSP					ok
				create capacitor battery on expansion board			///			buy 0 ohm jumpers 0603					ok
	remove part of switches from the 3rd pcb				OK			tantal 220 uF 16v 5 pieces					buy mini usb vartical – 10 pieces					ok

	move all components far from the edge of pcb				OK		Pcb traces crosstalk – check this topic					77
				on circuit diagram adjust all titles/texts					77
	on vibromotor pcb footprint mark + contact				OK
				sending PCB drawings to manufacturer place all 3 boards on single 100x100mm board					ok		leds consumes too much current
	trace all left components				OK
				number all contacts for all buttons and periphery					OK		make possibility to enable debug via HC06 – debug data goes to PC via serial0
	proveritj ne meshajet li ICSP socket soketu batarei				OK					HC06 connected to serial1
	meshajet, sdelal 90 deg – nado zakazatj I proveritj eshe raz				OK		Unmask behind part of 3rd PCB board copper					not needed
	Tested – looks ok					use thermoglue
				test cutoff dimentions for the 3rd board					OK
move HC-06 on uart 2 ( Serial 1 )					OK
make adjustments in circuit diagram					OK		add makefile with all – build compile program I t.d.					77
add adjustments to code					OK
test everything					OK		Solder 0 ohm resistors to leds – to disable tx/rx leds					OK

create separate layout pcb for HC-06					not needed
	create circuit diagram				not needed		add to readme tutorial how to set up bluetooth terminal					77
	create pcb				not needed
	etch pcb				not needed		add to makefile job for environment automatic setup/install					77
	solder all components				not needed
	test it				not needed		move OW_Bandit titles to opther places, because those places where they are will be cut off.					OK

Test – maybe usb charging socket is too short					ok
	tested -found SC				fixed

Test – maybe power button is too short					ok
	Tested – yes, a bit short – will leave as is

Rev.1.2

Titles ow_bandit power_unit board change places,like on mcu_unit_board
On small PCB pins from soldered components are too close to battery
Socket for ow_slave for soket na ibutton slave (na malenkoj plate) meshajet bataree
footpring for relay is too small
max17043	Necessary to order new from ebay – there are fake and its’s not working
mark on socket for battery where is +
for FPC1 and FPC2 mark numbers of contacts
make thicker traces
Near charging led place titles where what kind of outputs are – charging and ready

use caps / resistors nominals from nomenclature
Use serial/arallel connection if absent

Red and Green on led change places and write pinout

transistor Q5 was in SOT-523 package. Change to SOT-23

Make PCB shorter from iButton slave side for 2mm				Power board

Write pinout for ow_slave and ow_master sockets

capacitors C2 and C3 put away from each other
and for 2313 package choose larger footprint

coil L2 make footprint for 7x7 mm coil. Plave a bit aside from dc/dc ic

make transistor key for buzzer

Pcb holding screws are too close to battery socket and to one of battery holders

Make battery holding header footprint for 2mm (larger) – currently they are smaller

Assembly

Solder wires to iButton slave socket					ok
Solder wires to iButton host socket					ok
Solder components to MCU PCB					ok
solder all components on Power board					ok

find solution for battery holding
fix everything in the case					ok
Cut all necessary holes in the case					ok

make list of missing details and make order					ok

test charging diode – pins polarity				found mistakes	ok

glue the buzzer to the pcb					ok

check max17043 on sparkfun during the week					zz

protect wires for ow_slave with thermotube					ok

try burn firmware via icsp MCU					zz
	Current consumption 150 – 170 ma – probably SC somewhere

wash PCBs from flux					ok
Check Agnd and gnd					zz